## Read Me
Halo Experience Portal - Budget, Milestones and Forecast Workbook
Draft grant support workbook - figures are planning assumptions and require accountant/grant adviser validation.
Item | Draft position
Applicant | HaloNinjas Ltd - legal entity details to confirm
Project | Halo Experience Portal, working title subject to trademark/partner permission
Duration | 18 months
Indicative project cost | £1.025m
Indicative grant ask | £450k
Primary route | Scottish Enterprise R&D Grant, subject to adviser feedback
Workbook purpose | Provide a structured budget, work package, claim and commercial forecast pack for grant conversations.
Important caveat | Do not submit without confirming eligible costs, intervention rate, match funding and whether any project work has started.

## Funding Summary
Funding Summary
Primary funding case and headline metrics.
Metric | Value
Total indicative project cost
Assumed eligible cost base
Target grant rate | 45%
Indicative grant request
Required match funding
Project duration months | 18
Direct FTE by project end | 8
Target ARR by Year 5
Base case direct FTE by Year 5 | 25
Note on B5: Assumed eligible cost base excludes a placeholder £25k for items likely to be partly ineligible. Validate with grant adviser.
Note on B6: Target grant rate is an assumption for planning. Actual intervention rate depends on company size, eligible costs and grant route.
Note on B7: Indicative grant ask only. Do not submit before adviser review.

## Budget
Budget
Indicative project cost breakdown. Confirm grant eligibility before submission.
ID | Category | Cost item | Qty/FTE | Months | Monthly/Unit cost | Total cost | Eligibility assumption | Notes
B01 | Payroll | Product / Programme Lead | 0.6 | 18 | 6250 |  | Likely eligible if directly employed on R&D | Product ownership, grant governance, customer validation
B02 | Payroll | Technical Lead / Architect | 1 | 18 | 7500 |  | Likely eligible if directly employed on R&D | Architecture, integration strategy, secure SDLC
B03 | Payroll | Senior Full Stack Developers | 2 | 18 | 5833.33 |  | Likely eligible if directly employed on R&D | Core product engineering
B04 | Payroll | Front End / UX Engineer | 1 | 18 | 5416.67 |  | Likely eligible if directly employed on R&D | Portal UX, design system, accessibility
B05 | Payroll | Back End / API Developer | 1 | 18 | 5833.33 |  | Likely eligible if directly employed on R&D | Integration layer and APIs
B06 | Payroll | QA / Test Automation Engineer | 1 | 12 | 4583.33 |  | Likely eligible if directly employed on R&D | Automated testing, release quality
B07 | Payroll | UX / Product Designer | 0.5 | 12 | 5000 |  | Likely eligible if directly employed on R&D | Research, journey design, prototype testing
B08 | Payroll | DevOps / Security Engineer | 0.5 | 12 | 7083.33 |  | Likely eligible if directly employed on R&D | CI/CD, tenant security, monitoring
B09 | Specialist R&D | Security architecture and penetration testing | 1 | 1 | 30000 |  | Potentially eligible; confirm | Independent security validation
B10 | Specialist R&D | UX research and accessibility validation | 1 | 1 | 25000 |  | Potentially eligible; confirm | User testing and accessibility evidence
B11 | Specialist R&D | AI/search specialist support | 1 | 1 | 30000 |  | Potentially eligible; confirm | Knowledge retrieval and governance prototype
B12 | Specialist R&D | Technical grant / finance / audit support | 1 | 1 | 35000 |  | May be partly ineligible; confirm | Claims, evidence, reporting, technical writing
B13 | Cloud & tools | Cloud environments and test infrastructure | 1 | 18 | 2000 |  | Potentially eligible if directly tied to R&D | Dev, staging, pilot, monitoring, backups
B14 | Cloud & tools | Development tools, licences and devices | 1 | 1 | 34000 |  | Potentially eligible; confirm | Repos, testing tools, accessibility tools, devices
B15 | Pilot validation | Pilot onboarding and validation | 1 | 1 | 25000 |  | Potentially eligible; confirm | Pilot workshops, onboarding, support, measurement
B16 | Legal/IP/commercial | IP, trademark, DPA, SaaS terms and packaging | 1 | 1 | 25000 |  | Likely partly ineligible; confirm | Required for commercial launch readiness
B17 | Travel/workshops | Scottish workshops and ecosystem engagement | 1 | 1 | 12500 |  | May be restricted; confirm | Perth/Dundee/Inverness workshops
B18 | Project management | Project controls, reporting and quality governance | 1 | 1 | 30000 |  | Potentially eligible if direct project cost; confirm | PMO support and evidence pack
Total

## Grant Scenarios
Grant Scenarios
Indicative funding routes. Rates and eligibility must be confirmed with the grant body.
Scenario | Total project cost | Assumed eligible cost | Grant rate | Grant amount | Match funding | Notes
Primary SE R&D ask | 1025000 | 1000000 | 45% |  |  | Opening ask for Scottish Enterprise R&D discussion
Higher SME support case | 1025000 | 1000000 | 50% |  |  | Subject to eligibility, company size and grant body agreement
Reduced MVP route | 750000 | 735000 | 40% |  |  | Smaller team, reduced pilot and no AI/search strand
SE smaller R&D support | 150000 | 150000 | 35% |  |  | Only if eligible via SE account management/specialist support
SMART feasibility small company | 140000 | 140000 | 70% |  |  | Only if SMART/feasibility route is open
SMART feasibility medium company | 140000 | 140000 | 60% |  |  | Only if SMART/feasibility route is open

## Work Packages
Work Packages
Work package budget allocation and deliverables.
WP | Work package | Start month | End month | Budget allocation | Lead role | Key deliverables
WP1 | Discovery, architecture and validation | 1 | 2 | 90000 | Product Lead / Architect | Requirements, architecture decision record, pilot criteria
WP2 | Halo integration R&D | 2 | 6 | 165000 | Technical Lead | Reusable Halo connector, test harness, integration design
WP3 | Portal studio and design system | 2 | 8 | 165000 | UX Engineer | Branding, layout, widgets, configuration console
WP4 | Self-service modules | 4 | 11 | 205000 | Full Stack Team | Catalogue, tickets, approvals, knowledge, attachments
WP5 | Security, tenancy and operations | 5 | 13 | 135000 | DevOps/Security | Tenant model, audit, monitoring, security pack
WP6 | Knowledge and AI-assisted experience | 8 | 14 | 90000 | AI/Search Specialist | Search/AI prototype, governance, deflection analytics
WP7 | Pilot deployments | 10 | 16 | 115000 | Product Lead / QA | 3-5 pilots, feedback, validation evidence
WP8 | Commercialisation and launch readiness | 15 | 18 | 60000 | Project Sponsor | Pricing, partner pack, launch assets, support model
Total

## Milestones Gantt
Milestones and Gantt
Indicative 18-month plan. Green cells indicate active months.
WP | Work package | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
WP1 | Discovery, architecture and validation | bar: M1 to M2
WP2 | Halo integration R&D | bar: M2 to M6
WP3 | Portal studio and design system | bar: M2 to M8
WP4 | Self-service modules | bar: M4 to M11
WP5 | Security, tenancy and operations | bar: M5 to M13
WP6 | Knowledge and AI-assisted experience | bar: M8 to M14
WP7 | Pilot deployments | bar: M10 to M16
WP8 | Commercialisation and launch readiness | bar: M15 to M18
Milestone | Target month | M1: Evidence
Project mobilisation complete | 1 | M1: Team onboarding, governance, backlog
Architecture validated | 2 | M1: Architecture decision record and threat model
Halo connector alpha | 4 | M1: Auth and core mappings working
Portal framework alpha | 6 | M1: Branding, roles, widgets
MVP feature complete | 10 | M1: Catalogue, KB, tickets, approvals
Pilot readiness gate | 12 | M1: Security review and runbook
Pilot evidence complete | 16 | M1: Pilot metrics and feedback
Commercial launch gate | 18 | M1: Pricing, partner pack, support model

## Cashflow Claims
Cashflow and Grant Claims
Illustrative quarterly spend and claim profile. Many grants reimburse in arrears.
Quarter | Months | Planned spend | Cumulative spend | Grant receipt assumption | Company cash contribution this quarter | Cumulative company cash outflow before receipts | Notes
Q1 | M1-M3 | 150000 |  | 0 |  |  | Mobilisation, discovery, architecture, early connector
Q2 | M4-M6 | 180000 |  |  |  |  | Integration alpha and portal framework
Q3 | M7-M9 | 180000 |  |  |  |  | Core module development
Q4 | M10-M12 | 190000 |  |  |  |  | MVP feature complete and pilot readiness
Q5 | M13-M15 | 180000 |  |  |  |  | Pilots, AI/search refinement, validation
Q6 | M16-M18 | 145000 |  |  |  |  | Launch readiness and final evidence
Post-project receipt | After M18 | 0 |  |  |  |  | Final claim receipt if paid in arrears

## FTE Plan
FTE Plan
Indicative Scottish product team profile by month.
Role | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | Avg FTE
Product / Programme Lead | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
Technical Lead / Architect | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Senior Full Stack Developer 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Senior Full Stack Developer 2 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Front End / UX Engineer | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Back End / API Developer | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
QA / Test Automation Engineer | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
UX / Product Designer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DevOps / Security Engineer | 0 | 0 | 0 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25
Total FTE

## Revenue Forecast
Revenue Forecast
Base-case commercial planning forecast. Validate with customer discovery and accountant review.
Year | Paying customers | Average ARR per customer | SaaS ARR | Implementation / services revenue | Total revenue | Direct costs | Gross profit | Core opex | Indicative EBITDA | Direct FTE
Y1 build / pilots | 5 | 12000 |  | 15000 |  |  |  | 742500 |  | 8
Y2 launch | 30 | 8000 |  | 90000 |  |  |  | 600000 |  | 10
Y3 scale | 90 | 9000 |  | 220000 |  |  |  | 850000 |  | 15
Y4 international | 180 | 10000 |  | 360000 |  |  |  | 1200000 |  | 20
Y5 maturity | 300 | 12000 |  | 500000 |  |  |  | 1750000 |  | 25

## Risk Register
Risk Register
Working risk log for grant application and project governance.
ID | Risk | Likelihood | Impact | Score | Mitigation | Owner
R01 | Halo API changes or limitations | 3 | 5 |  | Abstraction layer, integration tests, version monitoring, partner comms | Technical Lead
R02 | Trademark / partner positioning risk | 3 | 5 |  | Use working title internally; confirm permission or neutral brand | Project Sponsor
R03 | Grant eligibility gaps | 3 | 5 |  | Engage adviser early; validate eligible costs and start-date rules | Project Sponsor
R04 | Scope creep into custom consultancy | 4 | 5 |  | MVP boundaries, product governance, template strategy | Product Lead
R05 | Security / tenant isolation issue | 3 | 5 |  | Threat model, pen test, secure SDLC, least privilege | Security Lead
R06 | Recruitment challenge | 3 | 3 |  | Hybrid roles, university links, contractor bridge | Product Lead
R07 | Pilot customers slow to engage | 3 | 3 |  | Letters of support and named pilot sponsors pre-application | Product Lead
R08 | Revenue slower than forecast | 3 | 4 |  | Stage-gated spend, partner validation, pricing tests | Project Sponsor
R09 | AI trust / data protection concern | 3 | 3 |  | Make AI optional, constrained, auditable and retrieval-led | Technical Lead
R10 | Insufficient match funding | 3 | 5 |  | Confirm match funding and cashflow capacity before submission | Project Sponsor

## Sources
Sources and Working Notes
Plain URLs used to prepare the pack. Check current pages again before submission.
Source | URL | Used for
Scottish Enterprise R&D Grants | https://www.scottish-enterprise.com/how-we-can-help/funding-and-grants/business-grants-and-funding-calls/research-and-development-grants | Primary grant fit, eligibility, minimum grant, economic impact, fair work/net zero
Find Business Support - Scottish Enterprise R&D grants | https://findbusinesssupport.gov.scot/service/funding/research-and-development-grants | Funding rates and grant minimum cross-check
Find Business Support - R&D project support | https://findbusinesssupport.gov.scot/service/funding/funding-to-support-research-and-development-projects | Smaller R&D support route
SMART: SCOTLAND | https://www.scottish-enterprise.com/how-we-can-help/funding-and-grants/business-grants-and-funding-calls/smart-scotland-grant | Feasibility fallback route, on-hold status, rates and cap
HIE Digital and Technology Adoption Grant | https://findbusinesssupport.gov.scot/service/funding/digital-and-technology-adoption-capital-grant | Inverness/HIE adjacent route and cost exclusions
Interface Standard Innovation Vouchers | https://interface-online.org.uk/vouchers/standard-innovation-vouchers/ | Academic collaboration seed funding
UKRI Innovate UK Smart Grants guidance | https://www.ukri.org/councils/innovate-uk/guidance-for-applicants/guidance-for-specific-funds/smart-innovation-funding-guidance/ | Innovate UK monitoring and assessment themes
Halo Service Solutions overview | https://haloservicesolutions.com/ | Halo product family and market context
HaloITSM features | https://usehalo.com/haloitsm/features/ | Halo self-service portal / knowledge / ITSM context
Halo API docs | https://haloitsm.com/apidoc/ | API integration basis